## Team Info
Team members
1 | Anuj SM | ASM
2 | Ritesh Kumar Singh | RKS
3 | RD Pradeekar | RDP
4 | Shreya CN | SCN
5 | Sindhu H | SH
6 | Himani Sahoo | HS
7 | Moulidhar B | MB
8 | Dinesh S | DS
9 | Moyukh Saha | MS

## Iteration (Sprint) Backlog
Sprint-1 Backlog
day 0 = initial estimate
Requirement | Task ID | Task Description | Responsible | Cum. Hours Spent | Status (Not Started / In Progress / Completed) | Hours of work remaining until completion
[7 empty] | Thu | Fri | Mon | Tue | Wed | Thu | In Progress
[6 empty] | Day | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | Not Started
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | Carry Over
|  |  | Team | 0 |  | 160 | 10 | 8 | 2 | 0 | 0 | 0 | Completed
REQ1 - Login/Register Pages
Designing Login Page | REQ1_T1 |  | HS |  | Completed | 3 | 1 | 1 | 1
Registeration page-Front end | REQ1_T2 |  | MB |  | Completed | 3 | 2 | 1
UI testing and routing | REQ1_T3 |  | MB |  | Completed | 2 | 1 | 1
backend code for Login and user credential verification | REQ1_T4 |  | RKS |  | In Progress | 2
backend code to receive registration request and forwarding to admin | REQ1_T5 |  | RDP |  | In Progress | 2
backend code for admin approval and authorization | REQ1_T6 |  | MS |  | Not Started | 2
Front end- Reset Password and New Password pages | REQ1_T7 |  | HS |  | Completed | 2 | 1 | 1
backend code for Reset Password and New Password pages | REQ1_T8 |  | ASM |  | Completed | 3 | 2 | 1
Junit and functional testing | REQ1_T9 |  |  |  |  | 5
REQ2 - Employee Dashboard
Designing Employee Dashboard Home page | REQ2_T1 |  | HS |  | In Progress | 3
Designing Seat booking pages | REQ2_T2 |  | MB |  | In Progress | 15
Design view status | REQ2_T3 |  | HS |  | In Progress | 6
Design notification bar/icon | REQ2_T4 |  | HS |  | Completed | 3 | 1 | 1 | 1
Design regularisation | REQ2_T5 |  | MB |  | In Progress | 4
UI testing and routing | REQ2_T6 |  | MB |  | In Progress | 2
backend code for seat availabilty | REQ2_T7 |  | RDP |  | Completed | 4 | 2 | 2
backend code for new seat booking | REQ2_T8 |  | RDP |  |  | 5
backend code for booking status | REQ2_T9 |  | MS |  |  | 3
backend code for employee profile | REQ2_T10 |  | MS |  |  | 2
backend code for notification | REQ2_T11 |  | SH |  |  | 2
backend code to send regular request | REQ2_T12 |  | SCN |  |  | 5
Junit and functional testing | REQ2_T13 |  |  |  |  | 7
REQ3 - Manager Dashboard
Designing Manager homepage | REQ3_T1 |  | MB |  |  | 2
Designing a approval page | REQ3_T2 |  | HS |  |  | 2
Designing employee list | REQ3_T3 |  | MB |  |  | 3
Rerouting to seat booking page for manager | REQ3_T4 |  | HS |  |  | 1
UI testing and routing | REQ3_T5 |  | HS |  |  | 2
backend code for manager profile | REQ3_T6 |  | SH |  |  | 2
backend code for list of employees | REQ3_T7 |  | SH |  |  | 2
backend code for a approval | REQ3_T8 |  | RKS |  |  | 7
Junit and functional testing | REQ3_T9 |  |  |  |  | 6
REQ4 - Admin Dashboard
Designing Admin Homepage | REQ4_T1 |  | HS |  |  | 3
Designing QR Code scanning page | REQ4_T2 |  | MB |  |  | 6
Designing Registration approval page | REQ4_T3 |  | HS |  |  | 2
Designing page to render reports (weekly and monthly) | REQ4_T4 |  | HS |  |  | 6
Designing a page to render seat booking and food opt-in counts | REQ4_T5 |  | MB |  |  | 3
UI testing and routing | REQ4_T6 |  | HS |  |  | 2
backend code for admin profile | REQ4_T7 |  | MS |  |  | 2
backend code for QR code scanning | REQ4_T8 |  | RDP |  |  | 4
backend code for registration approval | REQ4_T9 |  | ASM | Z |  | 3
backend code for generating reports(monthly and weekly) | REQ4_T10 |  | ASM |  |  | 8
backend code for food booking and seat booking counts | REQ4_T11 |  | SCN |  |  | 3
Junit and functional testing | REQ4_T12 |  |  |  |  | 6
Unplanned |  |  |  | 0
0
Total(IE) hours available for Spint-1 | 432
Total hours estimated for Sprint-1 | 160

## Idealized Burndown
Idealized Line | day: | 0 | 6
| Planned | 160 | 0
| Remaining | 160

## Release Plan
Sprint-1 Release
Iteration Release | Date | Project | Release Type | Release Features | Open Issues

## Planned Leaves
Team Member | Thu | Fri | Mon | Tue | Wed | Thu
| 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2023-03-30 | Leave
| 1 | 2 | 3 | 4 | 5 | 6 | On Duty
Anuj SM | [6 empty] | Holiday
Ritesh Kumar Singh | [6 empty] | Half Day
RD Pradeekar
Shreya CN
Sindhu H
Himani Sahoo
B Moulidhar
Dinesh S
Moyukh Saha

## Metrics
# | Start Date | End Date | Estimated Hrs | Actual Hrs (Planned + Unplanned) | Effort Deviation | Tasks Planned | Tasks Completed | Scope Coverage | Remarks
| 2023-03-23 | 2023-04-07 | 160 | 0 | #NAME? | 43 | 7