## Product Backlog
Final PoC Project- SMS (Secure My Seat) | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | 1 | 2
1
[7 empty] | 19 | 1 | 0
Application Management / Administration | [7 empty] | 1
1 | REQ1 | REQ1 - Login/Register Pages | [5 empty] | 1
|  |  | Designing Login Page | Release-1 | P2 | Completed | 3 | 1
|  |  | Registeration page-Front end | Release-1 | P2 | Completed | 3 | 1
|  |  | UI testing and routing | Release-1 | P3 | Completed | 2 | 1
|  |  | backend code for Login and user credential verification | Release-1 | P3 | Completed | 2 | 1
|  |  | backend code to receive registration request and forwarding to admin | Release-1 |  | Completed | 2 | 1
|  |  | backend code for admin approval and authorization | Release-1 | P1 | Completed | 2 | 1
|  |  | Front end- Reset Password and New Password pages | Release-1 |  | Completed | 2 | 1
|  |  | backend code for Reset Password and New Password pages | Release-1 | P1 | Completed | 3 | 1
1
2 | REQ2 | REQ2 - Employee Dashboard | [5 empty] | 1
|  |  | Designing Employee Dashboard Home page | Release-1 |  | Completed | 3 | 1
|  |  | Designing Seat booking pages | Release-1 |  | Completed | 7 | 1
|  |  | Design view status | Release-1 |  | Completed | 6 | 1
|  |  | Design notification bar/icon | Release-1 |  | In-Progress | 3 | 1
|  |  | Design regularisation | Release-1 |  | In-Progress | 4 | 1
|  |  | UI testing and routing | Release-1 |  | Completed | 2 | 1
|  |  | backend code for seat availabilty | Release-1 |  | Completed | 4 | 1
|  |  | backend code for new seat booking | Release-1 |  | Completed | 5 | 1
|  |  | backend code for booking status | Release-1 |  | Completed | 3 | 1
|  |  | backend code for employee profile | Release-1 |  | Completed | 2 | 1
|  |  | backend code for notification | Release-1 |  | Completed | 2 | 1
|  |  | backend code to send regular request | Release-1 |  | Completed | 5 | 1
|  |  | seat booking layout | Release-1 |  | Completed | 8 | 1
1
3 | REQ3 | REQ3 - Manager Dashboard | [5 empty] | 1
|  |  | Designing Manager homepage | Release-1 |  | Completed | 2 | 1
|  |  | Designing a approval page | Release-1 |  | Completed | 2 | 1
|  |  | Designing employee list | Release-1 |  | In-Progress | 3 | 1
|  |  | Rerouting to seat booking page for manager | Release-1 |  | Completed | 1 | 1
|  |  | UI testing and routing | Release-1 |  | Completed | 2 | 1
|  |  | backend code for manager profile | Release-1 |  | Completed | 2 | 1
|  |  | backend code for list of employees | Release-1 |  | Completed | 2 | 1
|  |  | backend code for a approval | Release-1 |  | Completed | 7 | 1
1
1
4 | REQ4 | Admin Dashboard | [5 empty] | 1
|  |  | Designing Admin Homepage | Release-1 |  | Completed | 3 | 1
|  |  | Designing QR Code scanning page | Release-1 |  | Completed | 6 | 1
|  |  | Designing Registration approval page | Release-1 |  | Completed | 2 | 1
|  |  | Designing page to render reports (weekly and monthly) | Release-1 |  | In-Progress | 6 | 1
|  |  | Designing a page to render seat booking and food opt-in counts | Release-1 |  | Completed | 3 | 1
|  |  | UI testing and routing | Release-1 |  | Completed | 2 | 1
|  |  | backend code for admin profile | Release-1 |  | Completed | 2 | 1
|  |  | backend code for QR code scanning | Release-1 |  | Completed | 4 | 1
|  |  | backend code for registration approval | Release-1 |  | Completed | 3 | 1
|  |  | backend code for generating repors(monthly and weekly) | Release-1 |  | Completed | 8 | 1
|  |  | backend code for food booking and seat booking counts | Release-1 |  | In-Progress | 3 | 1

## Burndown
Iteration | 0 | 2
Remaining | 19 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release