## Sprint-4.0 Retrospection
Project Name: Secure My Seat (Team-1)
Sprint - 1.0 |  | Date: 30-March-2023
# | +ve | r | Action Item | Target Date | Responsible
1 | 70% of the product backlog items are completed in Sprint - 1 itself | few task got carried over to the next sprint | for sprint 2 we have to properly estimate tha task | 07-April-2023 (Sprint - 2.0) | Team
2 | Team co-ordination is excellent | output not available through backend while writing JDBC query | By using response entity annotation | 07-April-2023 (Sprint - 2.0) | Team
3 | Equally distributed the task among team members | failed to give priority to the task | should be considered in sprint-2 | 07-April-2023 (Sprint - 2.0) | Team
4 | Reduced hourly estimation based on complexity of task | security conflict | added swagger url to permit all in security config | 07-April-2023 (Sprint - 2.0) | Team
5 | Good collaboration among team inorder to achieve integration
6